## Use Case & Time Comparison
TCS Agentic AI — End-to-End Cluster Upgrade Automation
USE CASE
Use Case Title: |  | Autonomous OpenShift Cluster Version Upgrade
Description: |  | An SRE or Platform Engineer initiates a cluster upgrade through the AI Chat interface by simply stating the target version (e.g., "Upgrade this cluster to 4.14.28"). TCS Agentic AI autonomously orchestrates the entire upgrade lifecycle — pre-flight health assessment, ITSM change management, safe execution with real-time monitoring, and post-upgrade verification with automated documentation — reducing 14–40 hours of manual SRE effort to under 10 minutes of human involvement per cluster.
KEY METRICS
Manual Effort (per cluster) |  |  | 14–40 hours
Human Time with Agentic AI |  |  | < 10 minutes
Time Saved |  |  | ~95%
Workflow Steps (Fully Automated) |  |  | 13 Steps
Automation Coverage |  |  | 90–95%
Audit & Compliance Trail |  |  | 100%
MANUAL PROCESS vs. TCS AGENTIC AI — TIME COMPARISON
# | Activity | Manual (SRE Time) | Automated (Agentic AI) | Saved | Mode
1 | Identify target version & validate upgrade path | 15–30 min | ~30 sec | 95% | AI
2 | Pre-upgrade health checks (Operators, nodes, etcd, certs, APIs, storage, PDBs) | 2–4 hours | 2–3 min | 97% | AI
3 | Blocker identification & remediation planning | 1–3 hours | ~1 min | 95% | AI
4 | Create ServiceNow Change Request (Justification, risk, rollback plan, attachments) | 1–2 hours | ~30 sec | 96% | AUTO
5 | Wait for CAB / manager approval | 4–24 hours | 0 min (auto-poll) | 100% | AUTO
6 | Dry-run validation & preflight checks | 30–60 min | 1–2 min | 95% | AUTO
7 | Execute upgrade & active monitoring (Watch CVO progress, operators, nodes for hours) | 2–4 hours | 0 min (autonomous) | 100% | AUTO
8 | Post-upgrade verification & smoke tests | 2–4 hours | 0 min (smart detect) | 100% | AI
9 | Generate post-assessment report (PDF/HTML) | 1–2 hours | 1–2 min | 96% | AI
10 | Close Change Request with documentation | 30–60 min | ~30 sec | 97% | AUTO
| TOTAL PER CLUSTER | 14–40 hours | < 10 minutes | ~95%

## Upgrade Workflow (13 Steps)
Automated Upgrade Workflow — Step by Step
When a user types "Upgrade this cluster to 4.14.28" in the AI Chat, the following 13-step workflow executes automatically:
Step | Title | Mode | What Happens | Duration
1 | User Request & Intent Recognition | USER | User types a natural language upgrade request in AI Chat. - AI parses message and identifies upgrade intent and target version - Extracts version number (e.g., 4.14.28) from free-form text - Confirms cluster context from active workspace selection | Instant
2 | Version Validation & Path Verification | AI | AI validates the target version and upgrade path. - Queries ClusterVersion to get current version - Checks upgrade channel graph for valid paths - Detects EUS-to-EUS upgrades and validates intermediate hops - Confirms target version is available in configured channel | ~30 sec
3 | Pre-Assessment — 50+ Health Checks | AI | AI runs comprehensive cluster health assessment in parallel. - Cluster Operators: all available, not degraded, not progressing - Node Health: all Ready, no resource pressure, no cordoned nodes - etcd: quorum, member count, leader stability, DB size - Certificates: check expiry within upgrade window - Deprecated APIs: scan for removed APIs in target version - Storage: PV capacity, CSI drivers, StorageClass health - Pod Disruption Budgets: validate PDB configuration - Networking: SDN/OVN, DNS, ingress controllers - Machine Config Pools: sync status, paused pools | 2–3 min
4 | Component Analysis & Blocker Identification | AI | AI analyzes health check results and identifies blockers. - Classifies each finding as Blocker, Warning, or Info - Assigns risk scores to each component - Generates overall upgrade readiness score - Produces PDF and HTML assessment reports | ~1 min
5 | Remediation Proposals | AI | For any blockers found, AI proposes targeted fix actions. - Each blocker gets a specific remediation action - Fix proposals include risk level and impact assessment - User can review and approve fixes via the UI - If no blockers found, this step auto-advances | ~30 sec
6 | ServiceNow Change Request Creation | AUTO | System auto-generates a fully populated ServiceNow CR. - CR populated with: description, justification, risk classification, rollback plan - PDF assessment report attached as evidence - HTML assessment report attached for easy viewing - CR category, priority, and assignment group auto-set | ~30 sec
7 | Approval Gate — Auto-Polling | GATE | System continuously polls ServiceNow for CR approval. - Polls ServiceNow API every 60 seconds for state changes - Auto-advances when CR reaches 'Approved' state - State machine pauses safely — no timeout, no data loss - Dashboard shows live CR status to the user | Auto-poll
8 | Dry Run Validation | AUTO | Final preflight validation before committing to upgrade. - Re-validates upgrade path is still available - Checks no new blockers appeared since pre-assessment - Verifies cluster state hasn't degraded during approval wait - Confirms all prerequisites still met | 1–2 min
9 | Execute Upgrade | AUTO | System initiates the CVO-driven cluster upgrade. - Patches ClusterVersion resource with target version - Records precise executedAt timestamp for audit trail - Updates ServiceNow CR with work notes: 'Upgrade initiated' - Transitions state machine to monitoring phase | ~30 sec
10 | Real-Time Progress Monitoring | AUTO | Continuous autonomous monitoring — zero human babysitting. - Polls ClusterVersion every 15 seconds for CVO progress % - Tracks operator health in real-time (available/degraded/progressing) - Monitors node readiness as nodes reboot during upgrade - Live dashboard shows progress bar, operator matrix, node status - Updates ServiceNow CR with periodic work notes on progress | 30–90 min (cluster-paced)
11 | Smart Completion Detection | AI | Upgrade marked complete ONLY when ALL 3 conditions met. - Condition 1: ClusterVersion history shows target version confirmed - Condition 2: ALL ClusterOperators are available and not degraded - Condition 3: ALL nodes are in Ready state - Records precise completedAt timestamp - Calculates and records total upgrade duration | Automatic
12 | Post-Assessment & Report Generation | AI | AI generates comprehensive post-upgrade assessment. - PDF Report: verified version, start/end timestamps, total duration - Operator health summary: total / available / degraded counts - Node health summary: total / ready counts - HTML Report with same data for web viewing - Both reports attached to ServiceNow CR | 1–2 min
13 | ServiceNow CR Closure | AUTO | System auto-closes the Change Request with full evidence. - Close notes include: upgrade start time, end time, total duration - Operator health: 'X of Y operators healthy' - Node health: 'X of Y nodes ready' - Post-assessment PDF and HTML attached as final evidence - CR state set to 'Closed - Successful' - Complete audit trail preserved for compliance | ~30 sec

## Multi-Cluster Scale
Multi-Cluster Impact at Scale
Environment Scale | Clusters | Manual Effort (per cycle) | With TCS Agentic AI | SRE Hours Reclaimed
Small Enterprise | 5 | 70–200 hours (1–2 weeks) | ~50 min human time + cluster upgrade time | ~68–198 hours saved
Medium Enterprise | 15 | 210–600 hours (2–4 weeks) | ~2.5 hrs human time + cluster upgrade time | ~207–597 hours saved
Large Enterprise | 50 | 700–2,000 hours (1–2 months) | ~8 hrs human time + cluster upgrade time | ~692–1,992 hours saved
Hyperscale | 100+ | 1,400–4,000 hours (2–4 months) | ~16 hrs human time + cluster upgrade time | ~1,384–3,984 hours saved
REAL-WORLD UPGRADE SCENARIOS
Scenario | Cluster Profile | Manual Duration | With TCS Agentic AI | Outcome
Minor Version Upgrade (4.14.x → 4.14.y) | 3 masters, 6 workers Production | ~16 hours (2 days) | ~8 min human + 45 min cluster | Zero blocker misses, CR auto-closed with full report
EUS-to-EUS Upgrade (4.12 → 4.14 via 4.13) | 3 masters, 12 workers Production | ~32 hours (3–5 days) | ~10 min human + 2.5 hrs cluster | Multi-hop path auto-validated, deprecated APIs caught
Fleet Rolling Upgrade (15 clusters) | Mixed sizes Dev + Staging + Prod | ~300 hours (2–3 weeks) | ~2.5 hrs human + cluster time | Rolling orchestration, per-cluster reports
Emergency CVE Patch (5 critical clusters) | 5 clusters Critical production | ~40 hours (expedited) | ~50 min human + cluster time | Fast-track assessment, expedited CR flow